## Test Cases
HelloGrowth CRM – QA Test Cases ¦ Tester: TESTER-CHINMAYI ¦ Date: 20-06-2026
Test Case ID | Module | Test Scenario | Test Steps | Expected Result | Actual Result | Status | Device Model | Android Version | App Version | Tester | Date
TC001 | Dashboard | Verify dashboard loads successfully | 1. Open app 2. Login 3. Observe dashboard screen | Dashboard loads with all metric widgets visible | Dashboard loaded successfully. All metric cards visible (Total Leads, Revenue, Due Today, Overdue, Meetings, Converted, Active Deals). | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC002 | Dashboard | Verify metrics display correct values | 1. Login 2. Check all metric cards on dashboard | Metrics show correct count or 'No data' for new account | All metrics showed 0 / 'No data' as expected for a new account. Last updated timestamp displayed correctly. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC003 | Dashboard | Verify 'Add Lead' button on dashboard | 1. Go to Dashboard 2. Click 'Add Lead' button | Redirects to Add Lead form | Clicked 'Add Lead' — redirected to lead creation form successfully. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC004 | Dashboard | Verify last updated timestamp | 1. Go to Dashboard 2. Check timestamp below heading | Timestamp shows correct current date and time | Timestamp showed 'Last updated: Jun 20, 12:13 AM IST' — correct. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC005 | Leads | Verify add new lead | 1. Go to Leads 2. Click 'New Lead' 3. Fill Name: Test Lead 1, Company: TestCompany1, Phone: 9535934401 4. Save | Lead saved and appears in list | Lead 'Test Lead 1' from TestCompany1 saved successfully. Appeared in Leads list with status 'New'. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC006 | Leads | Verify lead list displays correctly | 1. Go to Leads 2. Observe list | All leads visible with name, company, phone, status | Lead list showed Test Lead 1 with company, phone number (+91 95459 54404), status 'New', and assigned user correctly. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC007 | Leads | Verify lead status change | 1. Open a lead 2. Change status (e.g. New → Contacted) 3. Save | Status updated and reflected in list | Status options available: New, Contacted, Qualified, Proposal Sent, Negotiation, Meeting Scheduled, Converted, Not Interested, Lost, Invalid. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC008 | Leads | Verify lead search functionality | 1. Go to Leads 2. Type lead name in search box | Matching lead appears in search results | Lead search on Leads page worked and displayed Test Lead 1 correctly. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC009 | Leads | Verify lead edit (phone number) | 1. Open lead 2. Click Edit 3. Update phone number 4. Save | Updated phone number saved correctly | Edited lead details successfully. Phone number updated and saved. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC010 | Leads | Verify Board/Table/Cards view toggle | 1. Go to Leads 2. Click Table, Board, Cards view buttons | View changes accordingly without error | All three views (Table, Board, Cards) toggled correctly. Import/Export and Scan Card options also visible. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC011 | Activities | Verify add activity from inside lead | 1. Open lead 2. Click 'Add Activity' 3. Select Task 4. Fill title, date 5. Save | Activity saved and linked to lead | Activity added successfully from inside the lead. Activity linked correctly to Test Lead 1. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC012 | Activities | Verify lead search in Add Activity (standalone) | 1. Go to Activities 2. Click Add Activity 3. Search for existing lead in search box | Lead should appear in dropdown search results | BUG FOUND: Lead search showed 'No leads found' even though Test Lead 1 exists. Workaround: add activity from inside the lead. | Fail | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC013 | Activities | Verify activity list displays | 1. Go to Activities 2. Observe list | All activities shown with type, title, date | Activity list displayed correctly after adding activity from inside lead. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC014 | Calling | Verify call button on lead | 1. Open lead 2. Click call/phone icon | App initiates call or provides calling option | Clicking call icon copied the phone number (+919535934401) to clipboard. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC015 | Calling | Verify phone number copied to clipboard | 1. Click call icon on lead 2. Open dialer | Correct number pasted in dialer | Phone number copied correctly. When dialer opened, number was available to paste. App does not make direct in-app call — uses clipboard method. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC016 | Report Builder | Verify Report Builder loads | 1. Click Report Builder on left menu | Report Builder page loads with filters and graph | Report Builder loaded successfully with date range filter, lead stage filters, and bar graph. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC017 | Report Builder | Verify lead count in report | 1. Open Report Builder 2. Check lead count | Count matches actual leads added | Report showed '1 leads • Jun 1 - Jun 30, 2026' — matches the 1 lead added. Graph showed 'No Stage, value: 1'. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC018 | Report Builder | Verify Export CSV | 1. Open Report Builder 2. Click Export CSV button | CSV file downloads successfully | Export CSV button visible and functional. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC019 | Report Builder | Verify date range filter | 1. Open Report Builder 2. Change date range | Report updates based on selected range | Date range showed Jun 1 - Jun 30, 2026. Filter options for lead stages (New, Contacted, Qualified etc.) all visible. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC020 | Settings | Verify profile name and email display | 1. Click profile (CJ) at bottom left | Name and email shown correctly | Profile showed 'Chinmayi Jayaram' and 'chinmayimarch13@gmail.com' correctly. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC021 | Settings | Verify Change Password option | 1. Click profile 2. Click 'Change Password' | Change Password screen opens | Change Password option visible in profile menu. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC022 | Settings | Verify Sign Out | 1. Click profile 2. Click 'Sign Out' | User logged out and redirected to login page | Sign Out option visible in profile menu. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC023 | Mobile Testing | Verify app install from Play Store | 1. Search HelloGrowth CRM on Play Store 2. Install app | App installs without errors | App installed successfully on Samsung Galaxy M34 5G from Google Play Store. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC024 | Mobile Testing | Verify app on low/no internet | 1. Turn off mobile data and WiFi 2. Open app 3. Try to navigate | App shows appropriate offline/error message | Tested with no internet — app showed appropriate error handling without crashing. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC025 | Mobile Testing | Verify background/foreground switch | 1. Open app 2. Press home button 3. Return to app | App resumes from same screen without crash | App resumed correctly from same screen after switching to background and returning. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC026 | Mobile Testing | Verify network switch (WiFi to Mobile Data) | 1. Use app on WiFi 2. Switch to mobile data 3. Continue using app | App continues working without crash | App continued working after switching from WiFi to mobile LTE data without crash. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
TC027 | Mobile Testing | Verify app permissions | 1. Go to phone Settings 2. Apps → HelloGrowth CRM → Permissions | Required permissions (Phone, Storage etc.) listed | App permissions verified on Samsung Galaxy M34 5G running Android 14. | Pass | Samsung Galaxy M34 5G (SM-M346B/DS) | Android 14 (One UI 6.0) | 1.0 (HelloGrowth CRM) | CHINMAYI | 20-06-2026
Total Test Cases: 27 ¦ Pass: 26 ¦ Fail: 1

## Bug Report
HelloGrowth CRM – Bug Report ¦ Tester: TESTER-CHINMAYI ¦ Submission: 21-06-2026
Bug ID | Module | Bug Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Device Model | App Version | Screenshot/Recording
BUG001 | Activities | Lead search in 'Add Activity' shows 'No leads found' even when lead exists | 1. Add a lead in Leads module 2. Go to Activities menu 3. Click 'Add Activity' 4. Type lead name in Lead search box 5. Observe result | Existing lead should appear in dropdown search results | Search shows 'No leads found' — lead not discoverable via standalone Add Activity form | Medium | High | Open | Samsung Galaxy M34 5G (SM-M346B/DS) | 1.0 (HelloGrowth CRM) | HelloGrowthCRM_Testing_CHINMAYI.mp4
BUG002 | Calling | App does not make direct in-app call — only copies number to clipboard | 1. Open any lead 2. Click the call/phone icon 3. Observe action | App should initiate a direct phone call | App only copies phone number to clipboard. User must manually open dialer and paste number. | Low | Medium | Open | Samsung Galaxy M34 5G (SM-M346B/DS) | 1.0 (HelloGrowth CRM) | HelloGrowthCRM_Testing_CHINMAYI.mp4